## Sheet1
Main Task Name | Story / Task | Size | User Assigned (AB, IJ, JM, JK, MS, VM) | Days in Sprint / Effort Remaining | [7 empty] | Expected Effort | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
Example | As a <user> I want a <thing> so that I can <do this> | - | - | - | - | - | - | - | - | - | -
RSA Cryptosystem User Stories
Generate prime number | As a user, I want to be able to generate large prime numbers so that I can use them to create private and public keys | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Generate private and public key | As a user, I want to be able to generate a public and private key so that I can encrypt and decrypt messages | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Encode and decode a message | As a user, I want to be able to encode and decode a message using private and public keys so that I can securly send messages | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
RSA Attacking User Stories
Factor Public Key | As a user, I want to be able to use multiple public keys to find the desginer's private key by using a gcd function | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Decode Private Message | As a user, I want to use the private key that was found during factoring to decode the designer's meassage(s) | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Decrypt Private Message | As a user, I want to use an adaptive ciphertext attack to decrypt the designer's previously decoded private message | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LSB Image Stego User Stories
Embed bit in 1-LSB Monochrome plane | As a user, I want to be able to embed a bit into the 1-LSB plane so that I can send secret messages | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Extract bit in 1-LSB Monochrome plane | As a user, I want to be able to extract a bit from the 1-LSB plane so that I can decode secret messages | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Embed bit in 2-LSB Monochrome plane | As a user, I want to be able to embed a bit into the 2-LSB plane so that I can send secret messages | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Extract bit in 2-LSB Monochrome plane | As a user, I want to be able to extract a bit from the 2-LSB plane so that I can decode secret messages | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Embed bit in 1-LSB RGB plane | As a user, I want to be able to embed a bit into the 1-LSB plane so that I can send secret messages | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Extract bit in 1-LSB RGB plane | As a user, I want to be able to extract a bit from the 1-LSB plane so that I can decode secret messages | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Embed bit in 2-LSB RGB plane | As a user, I want to be able to embed a bit into the 2-LSB plane so that I can send secret messages | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Extract bit in 2-LSB RGB plane | As a user, I want to be able to extract a bit from the 2-LSB plane so that I can decode secret messages | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Find the PSNR | As a user, I want to know the peak signal to noise ratio (PSNR) so that I know the image quality of my produced image | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LSB Image Stego Attacking User Stories
Compare Original Images | As a user, I want to be able to compare images (or checksums) to see whether the image was modified | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Extract Data and Find Structure | As a user, I want to be able to extract data from the image and test it for structure | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Null Image Data | As a user, I want to be able to null over the image data to distroy any previous message | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SPRINT #1 |  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
|  |  |  | 15 | 15 | 14 | 10 | 7 | 7 | 7 | 0 | 15 | 12.86 | 10.71 | 8.57 | 6.43 | 4.29 | 2.14 | 0.00
Assign Roles | As a team, we want to assign specific agile roles so that we can work productivity | 1 | ALL | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Find A Testing Framework | As a team, we need to have a testing framework so that we can have effective test driven development | 4 | MS, VM | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0
Create A Backlog | As a developer, I want a graph of the burndown so that I can see our productivity | 2 | JK | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Create RSA Cryptosystem User Stories | As a developer, I want user stories of the RSA cryptosystem so that I can see what needs to be done | 2 | IJ | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create RSA Attacking User Stories | As a developer, I want user stories of the RSA Attacking so that I can see what needs to be done | 2 | AB | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create LSB Image Stego Attacking User Stories | As a developer, I want user stories of the stegonography attack so that I can see what needs to be done | 2 | JM | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create LSB Image Stego User Stories | As a developer, I want user stories of the stegonography so that I can see what needs to be done | 2 | JK | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
SPRINT # |  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00