## Sheet1
Main Task Name | Story / Task | Size | User Assigned (AB, IJ, JM, JK, MS, VM) | Days in Sprint / Effort Remaining | [7 empty] | Expected Effort | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
Example | As a <user> I want a <thing> so that I can <do this> | - | - | - | - | - | - | - | - | - | -
RSA Cryptosystem User Stories
RSA Attacking User Stories
LSB Image Stego User Stories
LSB Image Stego Attacking User Stories
New Stego User Stories
New Stego Attacking User Stories
Unplanned User Stories
Extract Data and Find Structure | As a user, I want to be able to extract data from the image and test it for structure | 4
Find the PSNR | As a user, I want to know the peak signal to noise ratio (PSNR) so that I know the image quality of my produced image | 4 | VM
SPRINT #4 |  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
|  |  |  | 23 | 21 | 20 | 16 | 15 | 8 | 2 | 0 | 23 | 19.71 | 16.43 | 13.14 | 9.86 | 6.57 | 3.29 | 0.00
RSA Cryptosystem User Stories
Encode and decode a message | As a user, I want to be able to encode and decode a message using private and public keys so that I can securly send messages | 4 | IJ | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pollard's Algorithm | As a user, I want to be able to attack RSA using Pollard's Algorithm | 3 | AB | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
Chinese Remainder Theorem | As a user, I want to be able to attack RSA using the Chinese Remainder Theorem | 3 | AB, MS | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0
Organize RSA | As a team, we need organize RSA files to be more organized | 4 | AB, IJ, MS | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0
New Stego User Stories
Extract message from Sudoku puzzle | As a user, I want to be able to extract a message hidden in a Sudoku puzzle | 4 | VM | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0
CSV Embed Message | As a user, I want to be able to embed a message into CSV file using # of spaces | 3 | JK | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0
CSV Extract Message | As a user, I want to be able to extract a message from a CSV file using # of spaces | 3 | JK | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0
CSV Attack | As a user, I want to be able to tell if there are cells with only spaces | 1 | JK | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
CSV Null Data | As a user, I want to be able to delete any cells with just spaces so as to remove any message | 1 | JK | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
SPRINT #3 |  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
|  |  |  | 21 | 21 | 21 | 14 | 13 | 9 | 6 | 1 | 21 | 18.00 | 15.00 | 12.00 | 9.00 | 6.00 | 3.00 | 0.00
RSA Cryptosystem User Stories
Generate private and public key | As a user, I want to be able to generate a public and private key so that I can encrypt and decrypt messages | 2 | AB, IJ, MS | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
Encode and decode a message | As a user, I want to be able to encode and decode a message using private and public keys so that I can securly send messages | 4 | AB, IJ, MS | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
Fermat Factorization | As a user, I want to be able to attack RSA using Fermat's Factorization | 3 | MS | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0
LSB Image Stego User Stories
Null Image Data | As a user, I want to be able to null over the image data to distroy any previous message | 2 | JK | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
New Stego User Stories
Create New Stego User Stories | As a developer team, we want user stories of the new stegonography so that we can see what needs to be done | 2 | JM, VM | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
Embed message into Sudoku puzzle | As a user I want to be able to send a solvable Sudoku puzzle with an embedded message | 4 | VM | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 0
Solve Sudoku Puzzle | I want a program that can solve sudoku puzzles in case the user cannot | 3 | JM | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Destroy Sudoku Message | I want to prevent others from using our sudoku puzzle by destroying/making the puzzle unsolvable | 3 | JM | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0
SPRINT #2 |  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
|  |  |  | 30 | 29 | 21 | 13 | 11 | 3 | 3 | 2 | 30 | 25.71 | 21.43 | 17.14 | 12.86 | 8.57 | 4.29 | 0.00
RSA Cryptosystem User Stories
Encode and decode a message | As a user, I want to be able to encode and decode a message using private and public keys so that I can securly send messages | 4 | AB, IJ, MS | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2
Generate prime number | As a user, I want to be able to generate large prime numbers so that I can use them to create private and public keys | 4 | AB, IJ, MS | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
LSB Image Stego User Stories
Compare Original Images | As a user, I want to be able to compare images to see whether the image was modified | 2 | JM, JK | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
Embed bit in 1-LSB Monochrome plane | As a user, I want to be able to embed a bit into the 1-LSB plane so that I can send secret messages | 3 | VM, JK | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
Embed bit in 2-LSB Monochrome plane | As a user, I want to be able to embed a bit into the 2-LSB plane so that I can send secret messages | 3 | VM, JK | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
Embed bit in 1-LSB RGB plane | As a user, I want to be able to embed a bit into the 1-LSB plane so that I can send secret messages | 3 | VM, JK | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
Embed bit in 2-LSB RGB plane | As a user, I want to be able to embed a bit into the 2-LSB plane so that I can send secret messages | 3 | VM, JK | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
Extract bit in 1-LSB Monochrome plane | As a user, I want to be able to extract a bit from the 1-LSB plane so that I can decode secret messages | 2 | VM, JK | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Extract bit in 2-LSB Monochrome plane | As a user, I want to be able to extract a bit from the 2-LSB plane so that I can decode secret messages | 2 | VM, JK | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Extract bit in 1-LSB RGB plane | As a user, I want to be able to extract a bit from the 1-LSB plane so that I can decode secret messages | 2 | VM, JK | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Extract bit in 2-LSB RGB plane | As a user, I want to be able to extract a bit from the 2-LSB plane so that I can decode secret messages | 2 | VM, JK | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
SPRINT #1 |  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
|  |  |  | 15 | 15 | 14 | 10 | 7 | 7 | 7 | 0 | 15 | 12.86 | 10.71 | 8.57 | 6.43 | 4.29 | 2.14 | 0.00
Assign Roles | As a team, we want to assign specific agile roles so that we can work productivity | 1 | ALL | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Find A Testing Framework | As a team, we need to have a testing framework so that we can have effective test driven development | 4 | MS, VM | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0
Create A Backlog | As a developer, I want a graph of the burndown so that I can see our productivity | 2 | JK | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Create RSA Cryptosystem User Stories | As a developer, I want user stories of the RSA cryptosystem so that I can see what needs to be done | 2 | IJ | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create RSA Attacking User Stories | As a developer, I want user stories of the RSA Attacking so that I can see what needs to be done | 2 | AB | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create LSB Image Stego Attacking User Stories | As a developer, I want user stories of the stegonography attack so that I can see what needs to be done | 2 | JM | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create LSB Image Stego User Stories | As a developer, I want user stories of the stegonography so that I can see what needs to be done | 2 | JK | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
SPRINT # |  |  |  | - | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00